## Slide 1
Preparation
Planning
Development & Release
Release Governance
Release Content
Release Comms
33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 01 | 02 | 03 | 04 | 05 | 06 | 07 | 08 | 09 | 10 | 11 | 12
Calendar Weeks
Overall Release 25.03 Timeline
Release Planning Prep
CX Roadmap Prep
BD/PD Roadmap Prep
Refinement
FOSS  Develop, Test & Release
16.09.24
Timeline & Milestones published
07.10.24
CX Release Roadmap Review
02.10.24
BD & PD Roadmap Review
16.10.24
Refinement
Day
28.10.24
Briefing Release Planning Guardrails & Boundary Conditions
14.11.24
Release Planning Gate
16.09.24
Town Hall Release Planning
R 25.03
10.10.24
Draft Roadmap
published
20.11.24
Results Release Planning
published
23.01.25
Start Opt-Out for standard candidates
Opt-Out
09.03.25
End Opt-Out
Release Finalization
e2e Test
28.10.24
Briefing Release Planning Gs & BCs
13.11 –
14.11.24
Release- Planning
(2 days)
25.10.24
Draft
Feature Freeze
17.01.25
Feature Freeze
/Kick off e2e
24.01.25
Test Freeze
KITs  Develop & Release
Standards  Develop & Release
07.02.25
Release Freeze
14.02.25
KIT initial PR
28.02.25
KIT final PR
15.11.24
Deadline standard request (in Houston)
20.12.25
Deadline for delivering standard candidate(in GitHub)
03.03.25
Deployment
Gate
17.03.25
Publish
Release
14.03.25
Deployment
Gate
11.03.25
Bundling
06.11.24
Refinement
Day